## Sheet1
08/14/15
08/17/15
-3		54	days as of June 21, 2015
		13	Lectures need to be written
		4.1538461538	Days per lecture (average)
		4	Days per lecture (planned)

			Due date
	mostly	Greeting
		Online course success
		Course introduction
	mostly	Materials
	mostly	Steel
	mostly	Aluminum
	Have material	Wood	06/25/15	Thu, Jun 25, 15
		Asphalt	06/29/15	Mon, Jun 29, 15
		Concrete	07/03/15	Fri, Jul 3, 15
		Masonry	07/07/15	Tue, Jul 7, 15
		Moisture	07/11/15	Sat, Jul 11, 15
		Flooring	07/15/15	Wed, Jul 15, 15
		Carpet	07/19/15	Sun, Jul 19, 15
		Gypsum	07/23/15	Thu, Jul 23, 15
		Paint	07/27/15	Mon, Jul 27, 15
		Glass	07/31/15	Fri, Jul 31, 15
		Plastics	08/04/15	Tue, Aug 4, 15
	begun	Class info	08/08/15	Sat, Aug 8, 15
	begun	Course Intro	08/12/15	Wed, Aug 12, 15

## Sheet2
Greeting
Course introduction
Online course success
Materials
Sustainability
Steel
Aluminum
Wood
Asphalt
Concrete
Masonry
Moisture
Flooring
Carpet
Gypsum
Paint
Glass
Plastics